## Instructions
ITC327W Project Progress and Contribution Workbook
Use this workbook throughout the semester. Update it after each project phase and submit the same workbook again so that progress can be tracked over time.
Sheet | Purpose | Evidence and Accountability Rules
Project Overview | Enter the group and project details. The dashboard summarises task progress automatically. | 1 | Every student must be assigned meaningful work in Microsoft Project.
Task Progress | Record planned and completed tasks, responsible students, dates, status, percentage completed and evidence. | 2 | Completed work must be supported by evidence such as GitHub activity, meeting records, document sections, screenshots or stakeholder communication.
Individual Contributions | Record the work personally completed by each student. Every entry must have evidence. | 3 | GitHub commits are not the only evidence. Planning, interviewing, documentation, coordination and quality review also count.
Stakeholder Engagement | Record meetings, calls and emails with the stakeholder and the main outcomes. | 4 | Do not record work as completed by a student when it was completed by someone else.
Challenges & Actions | Record project challenges, their effect and the corrective action taken. | 5 | Do not place passwords, API keys, identity numbers, private contact details or confidential records in this workbook or on GitHub.
Phase Summary | Provide a short summary of the phase, including achievements, outstanding work and participation concerns. | 6 | The confidential individual peer evaluation must be completed separately on Blackboard.
Group Reflection | Complete one shared reflection after each phase. Be honest and specific.
Recommended Update Points
|  | Unit 1 / Phase 1 | Planning, stakeholder engagement, requirements and initial SRS
|  | Phase 2 | Architecture, UML, ERD and interface design
|  | Phase 3 | Development, integration, testing and demonstration
|  | Final | Overall project summary and final reflection

## Project Overview
Project Overview and Progress Dashboard
Project Information | Group Response | Task Status | Count
Group name or number | Group U | Completed | 11
Project title | Sebenza Clocking System | In Progress | 0
Stakeholder or organisation | Umzamo Analytical Services | Not Started | 0
Group mentor | - | Delayed | 0
Reporting phase | Unit 1 / Phase 1 | Blocked | 0
Reporting period | 18 August 2026 - 4 September 2026 | Overdue | 0
Overall status | In Progress
Overall % complete | 100% | Contribution Summary | Count
Main achievement | Ensuring that stakeholders requirements were properly discussed, recorded and considered in the project planning | Contribution entries | 10
Main challenge | It was difficult to find a suitable time when all group members were available at the same time, which affected coordiination and meeting arrangements | Verified entries | 10
Next planned activity | Updating the project schedule , compile and organise Evidence and finalise SRS. | Unverified entries | 0
|  | Stakeholder engagements | 0

## Task Progress
Task Progress Tracker
Task ID | Reporting Phase | Activity | Task Description | Assigned Student | Start Date | Due Date | Status | % Complete | Evidence / Link | Verified by Group | Lecturer Comment | Progress Flag
U1-01 | Unit 1 / Phase 1 | Activity 1.1 | Identify and confirm the external stakeholder | Nkosinathi | 2026-08-18 | 2026-08-19 | Completed | 100 | Stakeholder meeting confirmation | Yes |  | Completed
U1-02 | Unit 1 / Phase 1 | Activity 1.1 | Document the current process and problem | lerato | 2026-08-21 | 2026-08-23 | Completed | 100 | Current process and problem analysis | Yes |  | Completed
U1-03 | Unit 1 / Phase 1 | Activity 1.1 | Define the project aim, objectives and scope | Takalani | 2026-08-24 | 2026-08-25 | Completed | 100 | Project aim, objectives and scope anaysis | Yes |  | Completed
U1-04 | Unit 1 / Phase 1 | Activity 1.2 | Prepare stakeholder interview questions | Thapelo | 2026-08-16 | 2026-08-17 | Completed | 100 | Interview Questions document | Yes |  | Completed
U1-05 | Unit 1 / Phase 1 | Activity 1.2 | Conduct and document the stakeholder interview | Pedro | 2026-08-18 | 2026-08-20 | Completed | 100 | Interview minutes | Yes |  | Completed
U1-06 | Unit 1 / Phase 1 | Activity 1.3 | Compile the initial SRS | Nkosinathi & Tshepiso | 2026-08-25 | 2026-08-30 | Completed | 100 | initial SRS document | Yes |  | Completed
U1-07 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Microsoft Project schedule | Selloane | 2026-08-19 | 2026-08-30 | Completed | 100 | Microsoft project schedule | Yes |  | Completed
U1-08 | Unit 1 / Phase 1 | Activity 1.3 | Create and configure the GitHub repository | kwanele | 2026-08-24 | 2026-08-24 | Completed | 100 | Github link | Yes |  | Completed
U1-09 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Supabase project | kwanele | 2026-08-25 | 2026-08-25 | Completed | 100 | Supabase setup screenshot | Yes |  | Completed
U1-10 | Unit 1 / Phase 1 | Activity 1.3 | Complete the progress report and contribution record | Paki & Tshepiso | 2026-08-18 | 2026-08-30 | Completed | 100 | progress tracker and contribution sheet | Yes |  | Completed
U1-11 | Unit 1 / Phase 1 | Activity 1.3 | Complete the Unit 1 group reflection | Tshegofatso | 2026-08-29 | 2026-08-30 | Completed | 100 | Unit 1 group reflection | Yes |  | Completed
Formulas:
Progress Flag = IF([Task Description]="","",IF([Status]="Completed","Completed",IF([Status]="Blocked","Blocked",IF([Status]="Delayed","Delayed",IF(AND([Due Date]<>"",[Due Date]<TODAY(),[Status]<>"Completed"),"Overdue","On Track")))))

## Individual Contributions
Individual Contribution Record
Student Name | Student Number | Reporting Phase | Activity | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Notes
Tshegofatso | 221008431 | Unit 1 / Phase 1 | 1.3 | Note - Taker during meeting & Reflection support | Recorded the processes followed by the group, took notes during meetings, and documented important decisions and discussions and kept track of activities. Assited with initial documentation, led group reflection, and Proof read initial SRS and phase summary | 2026-08-30 | 13 days | progress documentation and meeting notes. | Yes | 2026-08-30
Lerato | 221019628 | Unit 1 / Phase 1 | 1.1 | TimeKeeper during meeting and Process Documentation Support | documented the current process and problem identfied during Activity 1,1 | 2026-08-23 | 2 days | current process and problem analysis. | Yes | 2026-08-30
Nkosinathi | 222001265 | Unit 1 / Phase 1 | 1.1, 1.2, 1.3 | Meeting facilitator and SRS Lead | Contacted and communicated with the stakeholder, facilitated stakeholder engagement, and led the initial SRS using the requirements gathered during unit 1 | 2026-08-30 | 6 days | Stakeholder coommunication records and initial SRS sections | Yes | 2026-08-30
Selloane | 221003714 | Unit 1 / Phase 1 | 1.1 and 1.2 | Requirements Checker during meeting and Project Scheduling Support | Completed assigned Activity 1,1 work and supported the group with project planning and documentation during preparation of the unit 1 submission | 2026-08-30 | 11 days | Requirements review and Microsoft Project schedule | Yes | 2026-08-30
kwanele | 221049921 | Unit 1 / Phase 1 | 1.1 and 1.3 | Technical Setup Support | Created and configured the Github repository and created the initial Supabase project for the group, drafted feasability and risk register | 2026-08-25 | 1 day | GitHub repository and Supabase setup evidence | Yes | 2026-08-30
Thapelo | 222010648 | Unit 1 / Phase 1 | 1.1 and 1,2 | Stakeholder interview Question Lead | Prepare the stakeholder interview questions used to gather the requirements durimg Activity 1.2 | 2026-08-17 | 1 day | Stakeholder interview questions document | Yes | 2026-08-30
Paki | 221014841 | Unit 1 / Phase 1 | 1.1 and 1.2 | Progress Report and Contribution Record Lead | Compiled and updated the unit 1 progrss report and contribution record, working alongside Tshepiso to ensure member activities were captured | 2026-08-30 | 12 days | Progress tracker and individual record | Yes | 2026-08-30
Tshepiso | 223043312 | Unit 1 / Phase 1 | 1.2 and 1.3 | interview Documentation and SRS Support | assisted with the initial SRS, process documentation and the unit progress documentation | 2026-08-30 | 12 days | intial SRS and progress documentation | Yes | 2026-08-30
Pedro | 222078169 | Unit 1 / Phase 1 | 1.2 | Stakeholder interview Lead | Conduct and Document the stakeholder interview and captured the key information required for the project | 2026-08-20 | 4 hours | Stakeholder Answrs included in SRS | Yes | 2026-08-30
Takalani | 221014651 | Unit 1 / Phase 1 | 1.1 | Project aim, objectives and Scope lead | Defined the project aim, objectives and scope for the Sebenza Clocking System based on the identified stakeholder problem | 2026-08-25 | 1 day | Project aim , objectives and scope analysis | Yes | 2026-08-30

## Stakeholder Engagement
Stakeholder Engagement Record
Date | Reporting Phase | Type of Engagement | Purpose | Students Present | Stakeholder Present / Role | Main Findings | Action Required | Evidence / Link
2026/18/21 | Unit 1 / Phase 1 | Telephone Call | to identifiy the problems being faced by stakeholder and what can be done to fix that problem. Confirm their requirements. | All | HR | The Stakeholder explained that they are currently using a manual way to take attendence. He also explained the issue with this method which was that workers can record an earlier arrival time than their actual time creating a risk of payment for hours not worked | Stakeholders need us to create a more reliable and verifiable clock in process . A system that will improve the reliability of attendance records | questionnair proof in SRS

## Challenges & Actions
Challenges and Corrective Actions
Date Identified | Reporting Phase | Challenge | Effect on Progress | Corrective Action | Responsible Student | Target Date | Status
2026-08-18 | Unit 1 / Phase 1 | Finding a suitable stakeholder and arranging access to the stakeholder | The group had to wait until the stake holder was available before ut coukd confirm the way forward | chose a sakeholder willing to be interviewed even if their time was limited . | all | 2026-08-18 | Resolved
2026-08-20 | Unit 1 / Phase 1 | Working around the stakeholder's availability while also making sure the required group members could attend | The group could not rush the stakeholder and had to use the available meeting time. This caused a later start than originally intended and increased time pressure | Members who completed their own tasks supported members who still had outstanding work so that the group could continue progressing | all | 2026-08-30 | Resolved

## Phase Summary
Phase Progress Summary
Summary Information | Group Response | Phase Completion Checklist
Reporting phase | Unit 1 / Phase 1 | Initial or updated SRS completed | Yes
Reporting period |  | Progress report updated | Yes
Overall phase status | In Progress | Individual contributions recorded | Yes
What was completed during this phase? | We managed to Agree on which stakeholder to interview, identified the stakeholder's manual clocking system problem, we gathered preliminary requirements, prepared the initial SRS content, created the Microsoft Project Schedule , set up GitHub and Supabase and updated the progress and contribution records | Stakeholder engagement recorded | Yes
What remains incomplete? | The initial SRS and supportong evidence still require fnal consolidation and verification before the phase is fully complete | Challenges and actions updated | Yes
Why is it incomplete? | Documentation is still being checked aganinst the stakeholders findings and supporting evidence needs to be organised | Group reflection completed | Yes
Which contributions were particularly important? | Esuring that we get the requirements from the stakeholder because they gave us a clear understanding of the problem we were to fix | Microsoft Project updated | Yes
Were there participation concerns? | There were communication difficulties because one member did not initially have a reliable way to communicate with the group , another goup member who was nearby was able to share important information and communicate the tasks allocated to the that member | GitHub evidence available | Yes
What will the group improve in the next phase? | Use earlier internal deadlines, communicate task progress more consistently, collect evidence when tasks are completed and update the workbook continously | Confidential peer check completed | Yes
Main priority for the next phase | keeping the Microsoft Project Schedule up to date , making sure evidence for each contribution is available and to continue developing the system around the attendance verification problem and ensuring we set realistic timelines.

## Group Reflection
Group Reflection
Reflection Information | Group Response | Reflection Guidance
Reporting phase | Unit 1 / Phase 1 | Length | Approximately 300–400 words in total.
Project title | Sebenza Clocking System | Focus | Discuss the group’s actual experience, not the activity instructions.
Most important learning from this phase | The most important thing we learnt in this phase was that the system must be based on a real stakeholder problem,the stskeholder currently relies on manual employee clocking, which makes makes time difficult to verify.A worker could record an earlier arrival time than the time they actually arrived , which can result in payment for hours not worked . This showed the gorup why accurate requirements and stakeholder confirmation are important | Honesty | Identifying a genuine challenge will not disadvantage the group when an improvement action is provided.
What went well and why? | Stakeholder engagement, task allocation and the initial project seup went well. The group identified the main problem , gathered information from the stakeholder, divided responsibilities and started he SRS, Microsoft Progect chedule , GitHub repository and Supabase setup | Evidence | Ensure that claims about participation agree with the contribution record, Microsoft Project and GitHub.
What was difficult and why? | The main dffculty was coordinating work around he stakeholders availability and ensuring that information completed by one member was available to the others. The group also had to manage the different workbook records so that the task and contributions remained aligned | Research use | Student work may only be used for research after the required ethical approval and consent processes.
How were tasks divided among members? | Tasks were divided according to unit 1 activities and individual responsibilities. Nkosinathi led the stakeholder engagement and SRS work , Lerato documented the current ptocess, Takalani handled the project aim , objectives and scope , Thapelo prepared interview questions, Pedro conducted the stakeholder interview, Selloane handled project scheduling, Kwanele handled Github and Supabase setup, Tshepiso supported interview documntation and srs work , Paki supported the progress and contribution records and Tshegofatso supported note taking and the group reflection
Did all members contribute fairly? Explain. | The Group worked towards distributing meaningful responsibilities across all members. Each member was gven a defined responsibility and memebers supported one another when someone needed assitance. The contribution record reflects these responsibilities
How did the group handle disagreements or delays? | Delays were handled by communicating with affected members, clarifying what still needed to be done and providing support where becessary. When the stake holders availability affected the schedule th group used the availabile time and contnued preparing other work
What did the group learn from the stakeholder? | The group learned that the main issue is not simply recording attence digitally , th system must improve the reliability and verifiability of the clock n information. The stake holder current manual process can allow inaccurate arrival times to be recorded, which ca affect records and payment
Improvement action 1 for the next phase | Start tasks as soon as they are assgned and set earlier internal deadlines so that work is not rushed close to submission date
Improvement action 2 for the next phase | Update the progress tracker and organise evidence immediately after tasks are completed, while keepng the responsibilities and records consistent information across the entire workbook
Priority for the next phase | For the next phase the priority is to follow the project schedule , keep the progress records up to date and maintaing clear evidence for each completed task