## Instructions
ITC327W Phase 2 Project Progress Tracker
Use this workbook during Phase 2: System Architecture and Design. Update it throughout the phase and submit the same workbook with Assessment 2.
Sheet | Purpose | What must be kept current
Project Overview | Group details and automatic progress summary | Group information, GitHub link and current Phase 2 progress
Design Progress | Track each design artefact and supporting work | Architecture, UML, ERD, mobile/web interfaces, SRS and project-management tasks
Individual Contributions | Record work personally completed by each student | Activity, responsibility, work completed and evidence
Design Source Links | Record editable source links/files for submitted designs | Architecture, UML, ERD, mobile and web design sources
Challenges & Actions | Record design/project challenges and corrective action | Problem, effect, action, owner, target date and status
Phase Summary | Summarise what was achieved and what remains | Phase status, completed work, gaps and next priorities
Group Reflection | One shared group reflection for Phase 2 | Participation, collaboration, challenges, learning and improvements
Important
Do not create a separate tracker for each activity. This Phase 2 workbook is updated as the group progresses. Evidence may include GitHub commits, screenshots, document sections, editable design links/files and other appropriate project evidence. Do not include passwords, API keys or confidential stakeholder information.

## Project Overview
Phase 2 Project Overview
Group | Group U | Phase 2 Progress Summary
Project Title | Sebenza Clocking System | Total tracked items | 12
Stakeholder / Organisation | Umzamo Analytical Services | Completed | 12
Group Leader | Paki | In Progress | 0
Number of Group Members | 10 | Blocked | 0
GitHub Repository Link | https://github.com/biyasekwanele/sebenza-clocking-system.git | Average completion | 100%
Reporting Period | 14 September 2026 - 13 October 2026
Overall Phase Status | In Progress | Phase 2 Reminder
Phase 2 focuses on system architecture and design. Track the design artefacts, the editable source links/files, individual contributions, challenges, Microsoft Project updates and GitHub evidence. No separate stakeholder-evidence section is required in this tracker.

## Design Progress
Phase 2 Design Progress
Task ID | Design / Project Item | Description / Expected Output | Responsible Student(s) | Planned Date | Actual Completion Date | Status | % Complete | Evidence / Link | Notes / Action Required
P2-01 | System Architecture | Overall architecture showing Flutter, ASP.NET and shared Supabase backend | Tshegofatso | 2026-09-18 | Completed | Completed | 100% | https://viewer.diagrams.net/?tags=%7B%7D&lightbox=1&highlight=0000ff&edit=_blank&layers=1&nav=1&title=System%20Architecture.drawio&dark=auto#Uhttps%3A%2F%2Fdrive.google.com%2Fuc%3Fid%3D1rESYHt5o1iQarVEFVaAx0mJylvMq4XkD%26export%3Ddownload
P2-02 | Use Case Diagram | Actors, use cases, system boundary and appropriate UML relationships | Pedro & Takalani | 2026-09-18 | Completed | Completed | 100% | https://app.diagrams.net/#G1WnnMAADEEE-IsjPr1TTquf-2JKCgalI1#%7B%22pageId%22%3A%220YesyBUdXUmlOLOw5Ugs%22%7D
P2-03 | Sequence Diagram 1 | Important Flutter process | Lerato | 2026-09-21 | Completed | Completed | 100% | https://viewer.diagrams.net/?tags=%7B%7D&lightbox=1&highlight=0000ff&edit=_blank&layers=1&nav=1&title=Sequence%20Diagram.drawio&dark=auto#Uhttps%3A%2F%2Fdrive.google.com%2Fuc%3Fid%3D1Lxjyn7C33eKcqnTFqsEF9ZGF_tcGvsgr%26export%3Ddownload
P2-04 | Sequence Diagram 2 | Important ASP.NET process | Selloane | 2026-09-21 | Completed | Completed | 100% | https://viewer.diagrams.net/?tags=%7B%7D&lightbox=1&highlight=0000ff&edit=_blank&layers=1&nav=1&title=Sequence%20Diagram-Overtime.drawio&dark=auto#R%3Cmxfile%3E%3Cdiagram%20name%3D%22Page-1%22%20id%3D%22l3LJjRWJDzVEaLW4UUNY%22%3E7Zxbc5s4FIB%2FjWfSh2S4gx99S5tttsnGabrbl44Msk2DEQFhx%2Fn1KyGBuSVEtfHaXaczKRykI6FzPh1dUDrqYPH8MQTB%2FE%2FkQK%2BjSM5zRx12FEWRNI38RyVrJjEsiQlmoeswkbwRjN0XyIWpNHYdGBUSYoQ87AZFoY18H9q4IANhiFbFZFPkFUsNwAxWBGMbeFXpN9fBcya1FHMj%2FwTd2TwtWTa67MkE2I%2BzEMU%2BL8%2Bjic4dED6edRR1qI%2BsIWmaAbmWFfrvA8u2AGkZvJ2iOXDQKidSRx11ECKE2dXieQA92uZpc7J8l688zd4nhD5%2BT4bLu5up%2F2TCl7XiSOOnq6X%2B9eHcrGrhiiO8TpuO1Dygl%2FHCu3an0HN9ctcPYOguIIYheeJx8e1G1l%2FNXQzHAbBp1hVxKiKb44VH7mRySeyMAckS8nsnRME9CGeQVkNKEngeCCJ3klSDSkJox2HkLuEdjJh%2FUSmKMS16kPkNFQYoxEQS4ZCUQYUQRHgFI3LZ9%2BFq5BDfSF%2FQ7HcU4ymmdujD7EEm6qi9zU0En2Lo23BUk476QHrjuROwRK5zR2rn%2BrOCNqmQkrzSEjpvJEhcr5LCHNK3BCF2bTcAySsS8%2FRsjGjbk%2FdGj5mfK7RCYAK9fubKA%2BTRhEMfJbacup6XiogjS11d1%2FuZntyTfm9gDVWag5gvJx8lP7naMqPyu5xbJGLmYUvgxdzDuACGGD7nvJA78keISO5wTZLMc4gaqsXyrTY8p7DxTkrVuWrAe49ZpmpDCrngsAiAY53AOWJwxP29StRrBLxN2q%2Fx0RvfXnwZ3RPhNzghv3tBsDNkZIkzk4b6MkOa1RJD3RNDJ4b2xtA4DsAERJDiE5MatMWPpmt7ikGydALoBNDeALpFEZ6FcPzXdWvsGKa8L3Z4QdRlXp1QpTChOLRh8ywqB10OFdpMLpmH9sjE0SeyCcIYLai3%2Bk6PTmypzEP2Y8GB1WHVWauOyVljTsgxK9j2bT%2BoeJrU14ZGr%2BRXDpyC2MOZS%2BCU84axcWF8byQKyNjFmDFNTEDLKbRcigl9cM76CQKwJCvBM8uW8coU3QTQJ89vklZe0M79Di5duEpXBHg5xEdYUcXiiThXpToPDqEHMOm0Cg6R8%2BB0FaTOQRNtxMRgnUsQINKlRbnCbqlgg4BsqheKXqBA06SSvzOl9QpMszZzVgHmzTxTfr2gXBG9QRHzg4qiBMesBbcgVNkhodbBEio6VW%2BJ2e4emX0AnusATGGNYBS5iBIMfIfihrwjZFa1uhVmDUWAWcWszy0Mrao3KGobWnWH0Ha3hRbR4EAGpyCaZ7yRx3xx2vofBNytWa30Agm8ZIjLSJUSpRKZW8Fw6Uak%2BrWUvgL0u%2BFtldSuLkBqBTCeW5jUCvJlRW2TapzC6%2F4ITafqe4mv49H1aEAXC0n35yTzVwll42MDLOhc3p9EwVtoHmys1aXK%2BFhXLJFYaxm1uYUJNuQGRW0TbAoQfEwx9ECY3WdUva0hVfLcCB94PDVMq8iAKTLsNeX63OIoqg2K2kbR2geKv9cq0V5D4teATzhTvM4iDHAcJWu1hBG6ZASdH5N1SQDwh%2BMLkZplXJRGl6akiYRIQ6vNLc6lYr6tqGUu09Y%2BhcjjX%2BllCNNFos1ibxtk7g7DrlrBUBMZqZbDo1neif%2FV8FhR1DaGIku5JwyFMTT3iOF4jlbVsekO%2BeM%2BK11IkmI0ILnx9DQJmk4jWHBi4Q0YXStjm8703hs9zdrc4jswVoOitrHVBLBtfYnohPce8V6yLRq2NQOJBcJWYT%2BntGulseHWAVhRi18TWJbIPmoZY0szd4NxRdHuMH6R51cP8cMTmN4Afx19%2F7ReXZ6LUHyi8xjojLOhcDqLPeiBsFKaBXa1bcJpmntrDiuKWuZQ32E0PX1x9J%2FNQ8fxZOFSFQ60Xf7xwlkvCEJE%2BCHVgz%2Fph4z0I2qSRbLRYkGse4SrSLJe3N4wDJHoKStybW7xfVKpQVHL1Iqs7DZRmy55nsLsgSMOko96JRA7Lv7hodmBB9js24E0svHPcN6Hqi51a3MLo6opDYpaRrW7Q1RPXzQc0vbN1Zfx6O4%2BT%2BQZPf%2Bblq4MfLhK744w1Jb5tWSR3ZrsI%2FlSbnF%2B1QZFLfMrfJ7lMgQL6uINh1WS5ofhaAmpFRhT2x6%2B0Bu52%2B0JWeBhLhM7daFK1VMXplVafVGKds829bc5dfH5%2BzP%2B5%2Frpxx%2F258m38fzn%2BiX6%2B1x9j4HJ6%2BGiAevsWzRUzTlmLgK8j7ahz042lTvvhes4SU%2B8MYxUZ4HXvoSUhtk8oL6D%2BQWbVUxWOWSm7cli2u9ksZGXHP%2B78pfMdO3ZKz2EUW8uS9GFzUVuN38rgvW4mz%2FUoY7%2BBQ%3D%3D%3C%2Fdiagram%3E%3C%2Fmxfile%3E
P2-05 | ERD | Entities, attributes, PKs, FKs, relationships and cardinality | Kwanele & Paki | 2026-09-23 | Completed | Completed | 100% | https://lucid.app/lucidchart/bd59e6f9-8f1d-4421-8316-84cc445b37c5/edit?viewport_loc=-662%2C-448%2C5038%2C2106%2C0_0&invitationId=inv_1cb79b5c-175b-4651-a1bd-d4d0ac932d90
P2-06 | Flutter Interface Designs | Main mobile screens and navigation | Nkosinathi | 2026-09-22 | Completed | Completed | 100% | https://www.figma.com/make/ksSuk3HNqtRmwr8my3Dw7E/Sebenza-Clocking-System?code-node-id=0-6&p=f&fullscreen=1
P2-07 | ASP.NET Interface Designs | Main web pages and navigation | Nkosinathi | 2026-09-23 | Completed | Completed | 100% | https://www.figma.com/make/ksSuk3HNqtRmwr8my3Dw7E/Sebenza-Clocking-System?code-node-id=0-6&p=f&fullscreen=1
P2-08 | Design Alignment | Requirements linked across UML, ERD and interfaces | Kwanele & Paki | 2026-09-24 | Completed | Completed | 100% | https://lucid.app/lucidchart/bd59e6f9-8f1d-4421-8316-84cc445b37c5/edit?viewport_loc=-662%2C-448%2C5038%2C2106%2C0_0&invitationId=inv_1cb79b5c-175b-4651-a1bd-d4d0ac932d90
P2-09 | Updated SRS | Phase 2 architecture and design section inserted in existing SRS | Thapelo | 2026-09-30 | Completed | Completed | 100% | Updated SRS
P2-10 | Microsoft Project | Schedule updated to reflect design progress and upcoming development | Tshepiso | 2026-10-09 | Completed | Completed | 100% | Updated Project Tracker
P2-11 | GitHub | Current design documentation and repository organisation | Everyone | 2026-10-13 | Completed | Completed | 100% | https://github.com/biyasekwanele//sebenza-clocking-system.git
P2-12 | Phase 2 Presentation | Presentation and defence preparation | Everyone | 2026-09-13 | Completed | Completed | 100% | Powerpoint Presentation

## Individual Contributions
Phase 2 Individual Contributions
Student Name | Student Number | Activity / Artefact | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Quality / Review Notes | Contribution Status
Thapelo | 222010648 | 2.3 | Update the SRS | Upate all the typos, risk changelog and functional requirements also created the diagram links table. | 2026-09-15 | 1 day | Updated SRS | Yes | 2026-09-25 |  | Completed
Tshegofatso | 221008431 | 3.1 | System Architecture | Designed the system architecture. | 2026-09-18 | 4 days | https://viewer.diagrams.net/?tags=%7B%7D&lightbox=1&highlight=0000ff&edit=_blank&layers=1&nav=1&title=System%20Architecture.drawio&dark=auto#Uhttps%3A%2F%2Fdrive.google.com%2Fuc%3Fid%3D1rESYHt5o1iQarVEFVaAx0mJylvMq4XkD%26export%3Ddownload | Yes | 2026-09-25 |  | Completed
Pedro | 222078169 | 3.2 | Use Case | Developed the initial Use Case Diagram, identifying the main system actors and their interactions with the proposed system. | 2026-09-18 | 4 days | https://app.diagrams.net/#G1WnnMAADEEE-IsjPr1TTquf-2JKCgalI1#%7B%22pageId%22%3A%220YesyBUdXUmlOLOw5Ugs%22%7D | Yes | 2026-09-25 |  | Completed
Takalani | 221014651 | 3.2 | Use Case | Assisted with the Use Case Diagram following the group's design review and feedback, ensuring that the actors, use cases and system interactions remained aligned with the project requirements. | 2026-09-18 | 4 days | https://app.diagrams.net/#G1WnnMAADEEE-IsjPr1TTquf-2JKCgalI1#%7B%22pageId%22%3A%220YesyBUdXUmlOLOw5Ugs%22%7D | Yes | 2026-09-25 |  | Completed
Lerato | 221019628 | 3.2 & 3.3 | Sequence Diagram & Project Plan | Developed one of the Sequence Diagrams to illustrate the interaction between system components. Assisted with updating the project plan. | 2026-09-21 | 7 days | https://viewer.diagrams.net/?tags=%7B%7D&lightbox=1&highlight=0000ff&edit=_blank&layers=1&nav=1&title=Sequence%20Diagram.drawio&dark=auto#Uhttps%3A%2F%2Fdrive.google.com%2Fuc%3Fid%3D1Lxjyn7C33eKcqnTFqsEF9ZGF_tcGvsgr%26export%3Ddownload | Yes | 2026-09-25 |  | Completed
Selloane | 221003714 | 3.2 & 3.3 | Sequence Diagram & Project Plan | Developed one of the Sequence Diagrams to illustrate the interaction between system components. Assisted with updating the project plan. | 2026-09-21 | 7 days | https://viewer.diagrams.net/?tags=%7B%7D&lightbox=1&highlight=0000ff&edit=_blank&layers=1&nav=1&dark=auto#Uhttps%3A%2F%2Fdrive.google.com%2Fuc%3Fid%3D1eXohZenwZEWp6WhPrafkVnP-c2IGm0fk%26export%3Ddownload#%7B%22pageId%22%3A%22l3LJjRWJDzVEaLW4UUNY%22%7D | Yes | 2026-09-25 |  | Completed
Kwanele | 221049921 | 3.2 | Database Design and ERD | Designed the database structure and developed the Entity Relationship Diagram (ERD), identifying the main entities, attributes, keys and relationships required to support the system. | 2026-09-23 | 9 days | https://lucid.app/lucidchart/bd59e6f9-8f1d-4421-8316-84cc445b37c5/edit?viewport_loc=-662%2C-448%2C5038%2C2106%2C0_0&invitationId=inv_1cb79b5c-175b-4651-a1bd-d4d0ac932d90 | Yes | 2026-09-25 |  | Completed
Paki | 221014841 | 3.2 | Database Design and ERD | Assisted with the database design and developing the ERD | 2026-09-23 | 9 days | https://lucid.app/lucidchart/bd59e6f9-8f1d-4421-8316-84cc445b37c5/edit?viewport_loc=-662%2C-448%2C5038%2C2106%2C0_0&invitationId=inv_1cb79b5c-175b-4651-a1bd-d4d0ac932d90 | Yes | 2026-09-25 |  | Completed
Nkosinathi | 222001265 | 3.3 | User Interface Prototype | Designed the user interface prototypes , covering the proposed user-facing interfaces and ensuring that the designs support the system's functional requirements. | 2026-09-22 | 8 days | https://www.figma.com/make/ksSuk3HNqtRmwr8my3Dw7E/Sebenza-Clocking-System?code-node-id=0-6&p=f&fullscreen=1 | Yes | 2026-09-25 |  | Completed
Tshepiso | 223043312 | 3.3 | Project Tracker | Updated and maintained the Phase 2 project progress tracker, including the project overview, task progress and individual contribution records. | 2026-10-13 | 3 days | Updated Project Tracker | Yes | 2026-10-05 |  | Completed
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started

## Design Source Links
Phase 2 Original Design Source Links / Files
Design Artefact | Tool Used | Editable Link / File Name | Accessible to Lecturer? | Last Updated | Responsible Student | Included in SRS? | Notes
System Architecture | Draw.io | https://viewer.diagrams.net/?tags=%7B%7D&lightbox=1&highlight=0000ff&edit=_blank&layers=1&nav=1&title=System%20Architecture.drawio&dark=auto#Uhttps%3A%2F%2Fdrive.google.com%2Fuc%3Fid%3D1rESYHt5o1iQarVEFVaAx0mJylvMq4XkD%26export%3Ddownload | Yes | 2026-09-18 | Tshegofatso | Yes
Use Case Diagram | Draw.io | https://app.diagrams.net/#G1WnnMAADEEE-IsjPr1TTquf-2JKCgalI1#%7B%22pageId%22%3A%220YesyBUdXUmlOLOw5Ugs%22%7D | Yes | 2026-09-18 | Pedro & Takalani | Yes
Sequence Diagram 1 | Draw.io | https://viewer.diagrams.net/?tags=%7B%7D&lightbox=1&highlight=0000ff&edit=_blank&layers=1&nav=1&title=Sequence%20Diagram.drawio&dark=auto#Uhttps%3A%2F%2Fdrive.google.com%2Fuc%3Fid%3D1Lxjyn7C33eKcqnTFqsEF9ZGF_tcGvsgr%26export%3Ddownload | Yes | 2026-09-21 | Lerato | Yes
Sequence Diagram 2 | Draw.io | https://viewer.diagrams.net/?tags=%7B%7D&lightbox=1&highlight=0000ff&edit=_blank&layers=1&nav=1&dark=auto#Uhttps%3A%2F%2Fdrive.google.com%2Fuc%3Fid%3D1eXohZenwZEWp6WhPrafkVnP-c2IGm0fk%26export%3Ddownload#%7B%22pageId%22%3A%22l3LJjRWJDzVEaLW4UUNY%22%7D | Yes | 2026-09-21 | Selloane | Yes
ERD | LucidChart | https://lucid.app/lucidchart/bd59e6f9-8f1d-4421-8316-84cc445b37c5/edit?viewport_loc=-662%2C-448%2C5038%2C2106%2C0_0&invitationId=inv_1cb79b5c-175b-4651-a1bd-d4d0ac932d90 | Yes | 2026-09-23 | Kwanele & Paki | Yes
Flutter Interface Designs | Figma | https://www.figma.com/make/ksSuk3HNqtRmwr8my3Dw7E/Sebenza-Clocking-System?code-node-id=0-6&p=f&fullscreen=1 | Yes | 2026-09-22 | Nkosinathi | Yes
ASP.NET Interface Designs | Figma | https://www.figma.com/make/ksSuk3HNqtRmwr8my3Dw7E/Sebenza-Clocking-System?code-node-id=0-6&p=f&fullscreen=1 | Yes | 2026-09-22 | Nkosinathi | Yes
Navigation Flow | Figma | https://www.figma.com/make/ksSuk3HNqtRmwr8my3Dw7E/Sebenza-Clocking-System?code-node-id=0-6&p=f&fullscreen=1 | Yes | 2026-09-22 | Nkosinathi | Yes

## Challenges & Actions
Phase 2 Challenges and Corrective Actions
Date Identified | Challenge | Effect on Progress / Design | Corrective Action | Responsible Student | Target Date | Status | Resolved Date | Notes
2026-09-14 | Time and separation of tasks were difficult, and the group spent longer than expected deciding who should do which task. | Some time was lost before responsibilities were finalised. | we ended up just playing on each others strengths this time and just let people do tasks they enjoy and also some compromised where they had to as long as we get the task done. | Everyone | 2026-09-15 | Completed | 2026-09-15
2026-09-07 | Waiting on HR to reply with feedback on The updated SRS and wireframs | Could delay us compliting the SRS document as the feedback from the stakeholder is going to be the last thing on our list | Nkosinathi will follow up and gather the feedback atleast a week before we need to submit so that we can have enough time to look at the document in its final form fix what needs to be fixed and submit a well thought document | Nkosinathi | 2026-09-09 | Completed | 2026-09-09
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started

## Phase Summary
Phase 2 Progress Summary
Reporting Period | 14 September 2026 - 13 October 2026 | Phase 2 Completion Checklist | Complete?
Overall Phase Status | Completed | Architecture complete | Yes
What was completed during Phase 2? | We have succesfuly separated tasks among each other , the wireframes have been finished, the system archetecture, use case and sequence diagrams and ERD are completed. The SRS document is Up to date. | Use Case Diagram complete | Yes
What remains incomplete? | NONE | Two Sequence Diagrams complete | Yes
Why is it incomplete? | N/A | ERD complete | Yes
Which contributions were particularly important? | Ensuring that our diagrams explain what our system does properly | Flutter interfaces complete | Yes
Were there participation concerns? | Yes | ASP.NET interfaces complete | Yes
What will the group improve in Phase 3? | Communicate task progress more consistently and everyone be hands on to ensure success in our project. | Editable source links/files recorded | Yes
Main priority for Phase 3 | Finish the SRS, keep the GitHub repository and Microsoft Project file current, and prepare for the Phase 2 presentation. | SRS updated | Yes
|  | Microsoft Project updated | Yes
|  | GitHub current | Yes
|  | Individual contributions recorded | Yes
|  | Challenges/actions updated | Yes
|  | Group reflection completed | Yes

## Group Reflection
Phase 2 Group Reflection
1. What did the group complete successfully during Phase 2?
The group completed the main Phase 2 design artefacts recorded in the tracker, including the system architecture, Use Case Diagram, two Sequence Diagrams, ERD and user-interface prototypes. The group also made progress on the updated SRS, project planning and progress documentation.
2. Which architecture or design activities were the most challenging?
The most challenging Activity was getting the use case right. Also making sure that our wireframes include everything that was required.
3. How did the group ensure that Flutter, ASP.NET and Supabase were designed as one integrated system?
We gave each technology a clear responsibility: Flutter for the employee mobile interface, ASP.NET for the management web application and business logic, and Supabase for shared authentication and data storage. We then aligned the architecture, UML, ERD and interfaces so that they all represented the same requirements, data and processes.
4. How was work divided among group members, and was participation balanced?
Work was divided according to the Phase 2 responsibilities recorded in the contribution tracker. Nkosinathi worked on UI prototypes ; Pedro and Takalani on the Use Case Diagram; Lerato and Selloane on Sequence Diagrams and the project plan; Kwanele and Paki on the ERD; Tshegofatso on architecture and stakeholder engagement; Tshepiso on the progress tracker; and Thapelo on the SRS update. The group recorded that ten of ten members contributed fairly.
5. What did the group learn from developing the UML, ERD and interface designs?
We learned how to turn our Phase 1 requirements into technical designs. UML helped us understand system interactions, the ERD helped us structure the data, and the interface designs helped us translate the requirements into usable screens. We also learned the importance of keeping all our designs consistent.
6. What will the group do differently during development in Phase 3?
During development the group will communicate task progress more consistently, involve all members more actively, keep evidence and project records updated as work is completed, incorporate stakeholder feedback early and maintain realistic internal deadlines.